## Current State
Faculty Caucus Resolution Status Report: Smart Classrooms
(November 21, 2016)
Current State:
Technology Enabled Classroom Inventory: Total Number of Classrooms (All Classes): 73 Rooms
Room Classifications: Definitions
| Type 1 | Lectern with PC, projector, integrated audio system, network connectivity
| Type 2 | Lectern with PC, projector, non-integrated audio systems, network connectivity
| Type 3 | Projector, PC in room, network connectivity
| Type 4 | Projector, no audio system, cabling to Jack for Projector/PC connectivity
Inventory of Rooms
| Type 1 | 56
| Type 2 | 10
| Type 3 | 3
| Type 4 | 4
| Total | 73
Inventory of Classrooms:
|  |  | Total Teaching Spaces Scheduled by Registrar Spring 2015: | 124
|  |  | Total Teaching Scheduled by Registrar Spring 2015: | 125
|  |  | Total Number of Classrooms with Presentation Capability (All Types): | 73
|  |  | Percentage of Assigned Classrooms with Presentation Capability (All Types): | 58.4%
|  |  | Total Number of Registrar Scheduled Classrooms without Presentation Capability: | 52
|  |  | Percentage of Registrar Scheduled Classrooms without Presentation Capability: | 41.6%

## Timetable
Faculty Caucus Resolution Status Report: Smart Classrooms
(November 21, 2016)
Preliminary Timetable for Completion of all Assigned Teaching Spaces: 4 Year Plan
The target for teaching spaces on campus is to bring all teaching spaces to Type 2 capability.
within 4 years. This will enable all teaching spaces with installed Audio/Video capability,
resident PC, and network connectivity.
|  | Number of Registrar Scheduled Teaching Spaces without Presentation Capability: | 52
|  | Number of Registrar Scheduled Type 3 and Type 4 Teaching Spaces: | 7
|  | Total Number of Registrar Assigned Teaching Spaces to be Installed | 59
|  | Annual Rollout Requirement to Achieve 4 Year Completion: | 15

## Installation Activities
Faculty Caucus Resolution Status Report: Smart Classrooms
(November 21, 2016)
Instructional Space Technology Insatallation Activities: FY 2014 - FY 2016:
Smart Classroom Installations: FY 2014-FY2016: Rooms Developed - Total Rooms 18
|  |  | FY 2014 | FY 2015 | FY 2016
|  |  | AC-3H15 | AC-1C04 | AC-3H11A
|  |  | AC-1E03 | AC-1C05 | AC-3H11B
|  |  | AC-3C05 | AC-2B02 | AC 3H15
|  |  | AC-2C04 | AC-2C02 | AC-3H16
|  |  | AC-1E04 | AC-3C03
|  |  | AC-1C07 | AC-3G09
|  |  | AC-1A01 | AC-LL02
Student Instructional Technology Equipped Spaces Developed/Updated/Expanded: FY 2014-FY2016:
| Room | Action | Room Description
1 | AC-3G09 | Expanded/Updated | Library - Information Literacy Lab
2 | AC-1A01 | Updated | Fine Arts- Digital Design
3 | AC-LL02 | Developed | Fine Arts - Music Lab
4 | AC-2E03A | Updated | Computer Science/Math
5 | AC-2E03B | Updated | Computer Science/Math
6 | AC-1G02J | Updated | Center for Students with Disabilities - Computer Lab
7 | AC-1G07 | Developed | Center for Students with Disabilities - ADA Testing Lab
8 | AC-1G07A | Developed | Center for Students with Disabilities - ADA Testing Lab
9 | AC-1G07B | Developed | Center for Students with Disabilities - ADA Testing Lab
10 | AC-3G10 | Developed | YES Program Lab
11 | AC-2E09 | Updated | Physics - Lab
12 | AC-3H14 | Updated | Classroom - General Use
13 | CL-204A | Updated | Classroom - General Use
14 | CL-204B | Updated | Classroom - General Use
15 | CL-201B | Updated | Classroom - General Use
16 | CL-205 | Updated | Classroom - General Use
17 | CL-206 | Updated | Classroom - General Use
18 | SC-006 | Updated | Nursing - Lab

## Maintenance Activities
Faculty Caucus Resolution Status Report: Smart Classrooms
(November 21, 2016)
Instructional Space Technology Maintenance Activities: FY 2014 - FY 2016:
Smart Classroom Maintenance Activities: FY 2016 - FY2017
|  | Activity |  |  | Number
|  |  |  | Service Calls RESOLVED (June 2016- November 2016) | 130
|  |  |  | Surveys (Classroom/Lab/Lecture Halls) | 73
|  |  |  | Projector Filter Replacements or Cleaning | 55
|  |  |  | Projector Replacements | 4
|  |  |  | Lectern PC Replacements | 8 | (All lectern PCs < 3 years old)
|  |  |  | Project Screen Replacements | 1
|  |  |  | Remote Classroom Support Software Installations | 20
Onsite Replacement Equipment
|  | Projectors | 2
|  | Bulbs | 10
|  | Filters | On Order